## GANTT Chart
Milestones | Current progress | 2023 | [7 empty] | 2024 | [8 empty] | Not yet started
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | In progress
1. Thesis and other submission requirements | [18 empty] | Complete
1.1 Annotated Bibliography | [18 empty] | Deadline
1.1.1 Read wider review papers for context | Currently reading review papers | bar: 2023 May
1.1.2 Identify around 10 research papers (non-review) | 10 papers identified, to be cut down? | bar: 2023 May
1.1.3 Write annotations for the research papers | Annotations for 5 of the papers finished | bar: 2023 Jun
1.1.4 Submit annotated bibliography, and review with Mark | Done! (reviewed 23/06/2023) | 2023 Aug: 2023-08-31
1.2 Thesis Write-up
1.2.1 Outline of report prepared | Basic structure done | bar: 2023 May
1.2.2 Materials and Methods written up
1.2.3 Results written up
1.2.4 Discussion/Conclusion written
1.2.5 Introduction written up
1.2.6 Draft submission sent to Mark |  | 2024 Jul: 2023-07-31
1.2.7 Revisions to draft completed
1.2.8 Final Submission of Thesis to Moodle |  | 2024 Aug: TBC
1.3 Viva
1.3.1 Revision of methods and research techniques
1.3.2 Re-read referenced papers
1.3.3 Viva date |  | 2024 Sep: TBC
2. Bioinformatic tools and Automatic Domain Identification
2.1 Individual Tools and how they work
2.1.1 Chimera (re-learn) | bar: 2023 Jul
2.1.2 ConSurf
2.1.3 EVComplex2
2.1.4 Gremlin
2.1.5 k-means clustering: R package and how to use | Deep learning theory, will likely take a while.
2.2 Amidase_3 cell wall function recognition package
2.2.1 Reading into current tools for domain identification | To read up on: ECOD, how InterPro, SMART, SCOP and GO do their annotations, lit search for current methods in domain identification from sequence data (or structure/function data) | bar: 2023 Jul to 2023 Aug
2.2.2 Identifying where the amidase_3 domain is in a given sequence using identified functional residues | Develop as a python package? Rough this out using multiple sequence alignments across species with amidase_3 proteins to find conserved residues, then package can identify these regions (esp: conserved regions with a proven function)
(If time/feasible) Advance the above package | Maybe pattern recognition w/deep learning to identify the domain or similar features in other proteins? Could expand to other domains?
2.2.3 Testing the package | Run on positive control and negative control data sequences (see 3.2), make adjustments
3. Collect and organize information on NAMLAAs
3.1 Background research into NAMLAAs
3.1.1 Curate a current knowledge base of all papers regarding AmiC | bar: 2023 May
3.1.2 Quantify conservation between all amidase_3 solved structures | Multiple sequence alignment(s), look at RMSD (and also similarities in gram negative mobile region? Can I show this in theoretical structures as well if there is a difference?) | bar: 2023 Jun
3.1.3 NlpD research | Structure? Does it bind? Have assays confirmed it binds to AmiC? Theoretical docking models for NlpD and the AmiC structures
3.1.4 ActS research | Evidence for binding/function in relation to NAMLA (in E.coli especially?) Docking model? Compare to NlpD?
3.1.5 DolP research | Same as for ActS
3.2 Identifying regions associated with function of amidase_3 family proteins
3.2.1 Create a dataset of all protein structures with amidase_3 in PDB | Incl. GO annotation for functionality | bar: 2023 May
3.2.2 Confirm/identify which structures have a function in septal cell wall division | Positive control set - Start with the 19 amidase_3 orthologs - which are confirmed in literature? | bar: 2023 Jun
3.2.3 Confirm which structures do NOT have a function in septal cell wall division | Negative control set one - NAMLAAs which function elsewhere (ie eukaryotic NAMLAAs) | bar: 2023 Jun
3.2.4 Curate a negative dataset of non-NAMLAA enzymes involved in the cell wall division pathway | Negative control set two - EnvC, NlpD, ActS, DolP, FtsN, FtsZ, FtsA
3.2.5 Perform pairwise analysis of each structure to identify conserved regions | PDBeFOLD, Chimera MatchMaker, look for other tools. | bar: 2023 Jun
3.2.6 Confirm conserved regions have a role in function | Compare to tools like ECOD and other domain identification tools to see if any other methods might confirm these as residues, maybe docking analysis for structures with peptidoglycan and the LytM factors to see which residues are predicted to interact?
3.3 Creation of a test set and confirmation set for amidase_3 functionality (section 2.2.2)
3.3.1 All non-redundant sequences identified to contain amidase_3 domain | With note for which have alpha-fold structures as could be useful for confirming domain identification from sequence later - make sure sequences for the 19 structures above are filtered out to avoid confirmation bias | bar: 2023 Jun
3.3.2 All sequences across isolates identified to contain amidase_3 domain (training dataset?)
3.4 Filter sequence dataset to find which protein sequences are most likely to have NAMLAA cell wall division functionality specifically
3.4.1 Run package on all non-redundant sequences and output these sequences
3.4.2 Use AlphaFold predictions and PDB where available to examine the N-terminal domains and possible pathways/functions of these | Differences between gram positive and negatives? Between species? Any similarities?